## README
Experiment Matrix — Hybrid Graph-RAG for Medical QA (Journal Upgrade)
Conditions × Benchmarks × Backbones × Seeds, with a live run manifest and budget.
Purpose | A directly executable plan: every row of Run_Manifest is one job = (condition × benchmark × backbone × seed). A run processes all items in that benchmark at that seed.
How to use | 1) Pick a row in Run_Manifest. 2) Set Status (dropdown) and Owner; fill started/finished and result_path. 3) Budget_Summary and Live progress update automatically.
Unit of work | 1 run = 1 condition on 1 benchmark with 1 backbone at 1 seed. Item-level outputs are stored as JSONL/Parquet at result_path.
Sheets | Run_Manifest (the matrix) · Conditions · Benchmarks · Backbones · Metrics · Statistics · Budget_Summary (live) · Gates.
Contributions tracked | C1 RGD (decomposition) · C2 CA-RRF (concept fusion) · C3 CARe (adaptive reranking). Headline arm = Hybrid-CARRF-CARe.
Priority tiers | P0 = main comparison (3 seeds, all benchmarks, primary backbone). P1 = model-zoo / RGD generality. P2 = ablations.
Status legend | Pending · Ready · Running · Done · Failed · Blocked (color-coded in Run_Manifest column I).
Cost model | est_tokens = n_items × tokens/item × ctx_factor; est_cost = est_tokens/1e6 × rate. Rates are blended per-1M-token estimates (Backbones sheet) — not vendor quotes.
Key gates | Clinical arm depends on R1 (MIMIC governance) resolved by Day 5. Graph conditions depend on G3 (grounded graph) frozen at Day 20.
Companion docs | Doc 1: Enriched Experiments & Reframed Contributions · Doc 2: 50-Day Plan (hardware, complexity) · Doc 3: Paper Structure & Skeleton.
Note | Figures are planning estimates; treat them as a budget envelope, refine against actual provider pricing and rate limits.

## Run_Manifest
run_id | priority | phase | track | condition | backbone | benchmark | seed | status | owner | started | finished | fusion | rerank | grounding | retr_depth_k | ctx_factor | n_items | tokens/item | est_tokens | rate $/M | est_cost $ | depends_on | result_path | notes
R0001 | P0 | P2 | T2 | No-RAG | Llama-70B | MMLU-Med | 42 | Pending |  |  |  | — | off | off | — | 0.05 | 1089 | 4500 | 245025 | 0.6 | 0.14702 | H2 (harness)
R0002 | P0 | P2 | T2 | No-RAG | Llama-70B | MMLU-Med | 123 | Pending |  |  |  | — | off | off | — | 0.05 | 1089 | 4500 | 245025 | 0.6 | 0.14702 | H2 (harness)
R0003 | P0 | P2 | T2 | No-RAG | Llama-70B | MMLU-Med | 7 | Pending |  |  |  | — | off | off | — | 0.05 | 1089 | 4500 | 245025 | 0.6 | 0.14702 | H2 (harness)
R0004 | P0 | P2 | T2 | No-RAG | Llama-70B | MedQA-US | 42 | Pending |  |  |  | — | off | off | — | 0.05 | 1273 | 5000 | 318250 | 0.6 | 0.19095 | H2 (harness)
R0005 | P0 | P2 | T2 | No-RAG | Llama-70B | MedQA-US | 123 | Pending |  |  |  | — | off | off | — | 0.05 | 1273 | 5000 | 318250 | 0.6 | 0.19095 | H2 (harness)
R0006 | P0 | P2 | T2 | No-RAG | Llama-70B | MedQA-US | 7 | Pending |  |  |  | — | off | off | — | 0.05 | 1273 | 5000 | 318250 | 0.6 | 0.19095 | H2 (harness)
R0007 | P0 | P2 | T2 | No-RAG | Llama-70B | MedMCQA | 42 | Pending |  |  |  | — | off | off | — | 0.05 | 4183 | 4500 | 941175 | 0.6 | 0.56471 | H2 (harness)
R0008 | P0 | P2 | T2 | No-RAG | Llama-70B | MedMCQA | 123 | Pending |  |  |  | — | off | off | — | 0.05 | 4183 | 4500 | 941175 | 0.6 | 0.56471 | H2 (harness)
R0009 | P0 | P2 | T2 | No-RAG | Llama-70B | MedMCQA | 7 | Pending |  |  |  | — | off | off | — | 0.05 | 4183 | 4500 | 941175 | 0.6 | 0.56471 | H2 (harness)
R0010 | P0 | P2 | T2 | No-RAG | Llama-70B | PubMedQA | 42 | Pending |  |  |  | — | off | off | — | 0.05 | 500 | 5500 | 137500 | 0.6 | 0.0825 | H2 (harness)
R0011 | P0 | P2 | T2 | No-RAG | Llama-70B | PubMedQA | 123 | Pending |  |  |  | — | off | off | — | 0.05 | 500 | 5500 | 137500 | 0.6 | 0.0825 | H2 (harness)
R0012 | P0 | P2 | T2 | No-RAG | Llama-70B | PubMedQA | 7 | Pending |  |  |  | — | off | off | — | 0.05 | 500 | 5500 | 137500 | 0.6 | 0.0825 | H2 (harness)
R0013 | P0 | P2 | T2 | No-RAG | Llama-70B | BioASQ-YN | 42 | Pending |  |  |  | — | off | off | — | 0.05 | 618 | 5000 | 154500 | 0.6 | 0.0927 | H2 (harness)
R0014 | P0 | P2 | T2 | No-RAG | Llama-70B | BioASQ-YN | 123 | Pending |  |  |  | — | off | off | — | 0.05 | 618 | 5000 | 154500 | 0.6 | 0.0927 | H2 (harness)
R0015 | P0 | P2 | T2 | No-RAG | Llama-70B | BioASQ-YN | 7 | Pending |  |  |  | — | off | off | — | 0.05 | 618 | 5000 | 154500 | 0.6 | 0.0927 | H2 (harness)
R0016 | P0 | P2 | T2 | No-RAG | Llama-70B | GraphRAG-Bench-Med | 42 | Pending |  |  |  | — | off | off | — | 0.05 | 50 | 8000 | 20000 | 0.6 | 0.012 | H2 (harness)
R0017 | P0 | P2 | T2 | No-RAG | Llama-70B | GraphRAG-Bench-Med | 123 | Pending |  |  |  | — | off | off | — | 0.05 | 50 | 8000 | 20000 | 0.6 | 0.012 | H2 (harness)
R0018 | P0 | P2 | T2 | No-RAG | Llama-70B | GraphRAG-Bench-Med | 7 | Pending |  |  |  | — | off | off | — | 0.05 | 50 | 8000 | 20000 | 0.6 | 0.012 | H2 (harness)
R0019 | P0 | P2 | T2 | No-RAG | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | — | off | off | — | 0.05 | 200 | 8000 | 80000 | 0.6 | 0.048 | H2 (harness)
R0020 | P0 | P2 | T2 | No-RAG | Llama-70B | Clinical-Set | 123 | Pending |  |  |  | — | off | off | — | 0.05 | 200 | 8000 | 80000 | 0.6 | 0.048 | H2 (harness)
R0021 | P0 | P2 | T2 | No-RAG | Llama-70B | Clinical-Set | 7 | Pending |  |  |  | — | off | off | — | 0.05 | 200 | 8000 | 80000 | 0.6 | 0.048 | H2 (harness)
R0022 | P0 | P2 | T2 | No-RAG | Llama-70B | OverRefusal | 42 | Pending |  |  |  | — | off | off | — | 0.05 | 150 | 6000 | 45000 | 0.6 | 0.027 | H2 (harness)
R0023 | P0 | P2 | T2 | No-RAG | Llama-70B | OverRefusal | 123 | Pending |  |  |  | — | off | off | — | 0.05 | 150 | 6000 | 45000 | 0.6 | 0.027 | H2 (harness)
R0024 | P0 | P2 | T2 | No-RAG | Llama-70B | OverRefusal | 7 | Pending |  |  |  | — | off | off | — | 0.05 | 150 | 6000 | 45000 | 0.6 | 0.027 | H2 (harness)
R0025 | P0 | P2 | T2 | BM25 | Llama-70B | MMLU-Med | 42 | Pending |  |  |  | — | off | off | 32 | 0.9 | 1089 | 4500 | 4410450 | 0.6 | 2.6463 | H2 (harness)
R0026 | P0 | P2 | T2 | BM25 | Llama-70B | MMLU-Med | 123 | Pending |  |  |  | — | off | off | 32 | 0.9 | 1089 | 4500 | 4410450 | 0.6 | 2.6463 | H2 (harness)
R0027 | P0 | P2 | T2 | BM25 | Llama-70B | MMLU-Med | 7 | Pending |  |  |  | — | off | off | 32 | 0.9 | 1089 | 4500 | 4410450 | 0.6 | 2.6463 | H2 (harness)
R0028 | P0 | P2 | T2 | BM25 | Llama-70B | MedQA-US | 42 | Pending |  |  |  | — | off | off | 32 | 0.9 | 1273 | 5000 | 5728500 | 0.6 | 3.4371 | H2 (harness)
R0029 | P0 | P2 | T2 | BM25 | Llama-70B | MedQA-US | 123 | Pending |  |  |  | — | off | off | 32 | 0.9 | 1273 | 5000 | 5728500 | 0.6 | 3.4371 | H2 (harness)
R0030 | P0 | P2 | T2 | BM25 | Llama-70B | MedQA-US | 7 | Pending |  |  |  | — | off | off | 32 | 0.9 | 1273 | 5000 | 5728500 | 0.6 | 3.4371 | H2 (harness)
R0031 | P0 | P2 | T2 | BM25 | Llama-70B | MedMCQA | 42 | Pending |  |  |  | — | off | off | 32 | 0.9 | 4183 | 4500 | 16941150 | 0.6 | 10.1647 | H2 (harness)
R0032 | P0 | P2 | T2 | BM25 | Llama-70B | MedMCQA | 123 | Pending |  |  |  | — | off | off | 32 | 0.9 | 4183 | 4500 | 16941150 | 0.6 | 10.1647 | H2 (harness)
R0033 | P0 | P2 | T2 | BM25 | Llama-70B | MedMCQA | 7 | Pending |  |  |  | — | off | off | 32 | 0.9 | 4183 | 4500 | 16941150 | 0.6 | 10.1647 | H2 (harness)
R0034 | P0 | P2 | T2 | BM25 | Llama-70B | PubMedQA | 42 | Pending |  |  |  | — | off | off | 32 | 0.9 | 500 | 5500 | 2475000 | 0.6 | 1.485 | H2 (harness)
R0035 | P0 | P2 | T2 | BM25 | Llama-70B | PubMedQA | 123 | Pending |  |  |  | — | off | off | 32 | 0.9 | 500 | 5500 | 2475000 | 0.6 | 1.485 | H2 (harness)
R0036 | P0 | P2 | T2 | BM25 | Llama-70B | PubMedQA | 7 | Pending |  |  |  | — | off | off | 32 | 0.9 | 500 | 5500 | 2475000 | 0.6 | 1.485 | H2 (harness)
R0037 | P0 | P2 | T2 | BM25 | Llama-70B | BioASQ-YN | 42 | Pending |  |  |  | — | off | off | 32 | 0.9 | 618 | 5000 | 2781000 | 0.6 | 1.6686 | H2 (harness)
R0038 | P0 | P2 | T2 | BM25 | Llama-70B | BioASQ-YN | 123 | Pending |  |  |  | — | off | off | 32 | 0.9 | 618 | 5000 | 2781000 | 0.6 | 1.6686 | H2 (harness)
R0039 | P0 | P2 | T2 | BM25 | Llama-70B | BioASQ-YN | 7 | Pending |  |  |  | — | off | off | 32 | 0.9 | 618 | 5000 | 2781000 | 0.6 | 1.6686 | H2 (harness)
R0040 | P0 | P2 | T2 | BM25 | Llama-70B | GraphRAG-Bench-Med | 42 | Pending |  |  |  | — | off | off | 32 | 0.9 | 50 | 8000 | 360000 | 0.6 | 0.216 | H2 (harness)
R0041 | P0 | P2 | T2 | BM25 | Llama-70B | GraphRAG-Bench-Med | 123 | Pending |  |  |  | — | off | off | 32 | 0.9 | 50 | 8000 | 360000 | 0.6 | 0.216 | H2 (harness)
R0042 | P0 | P2 | T2 | BM25 | Llama-70B | GraphRAG-Bench-Med | 7 | Pending |  |  |  | — | off | off | 32 | 0.9 | 50 | 8000 | 360000 | 0.6 | 0.216 | H2 (harness)
R0043 | P0 | P2 | T2 | BM25 | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | — | off | off | 32 | 0.9 | 200 | 8000 | 1440000 | 0.6 | 0.864 | H2 (harness)
R0044 | P0 | P2 | T2 | BM25 | Llama-70B | Clinical-Set | 123 | Pending |  |  |  | — | off | off | 32 | 0.9 | 200 | 8000 | 1440000 | 0.6 | 0.864 | H2 (harness)
R0045 | P0 | P2 | T2 | BM25 | Llama-70B | Clinical-Set | 7 | Pending |  |  |  | — | off | off | 32 | 0.9 | 200 | 8000 | 1440000 | 0.6 | 0.864 | H2 (harness)
R0046 | P0 | P2 | T2 | BM25 | Llama-70B | OverRefusal | 42 | Pending |  |  |  | — | off | off | 32 | 0.9 | 150 | 6000 | 810000 | 0.6 | 0.486 | H2 (harness)
R0047 | P0 | P2 | T2 | BM25 | Llama-70B | OverRefusal | 123 | Pending |  |  |  | — | off | off | 32 | 0.9 | 150 | 6000 | 810000 | 0.6 | 0.486 | H2 (harness)
R0048 | P0 | P2 | T2 | BM25 | Llama-70B | OverRefusal | 7 | Pending |  |  |  | — | off | off | 32 | 0.9 | 150 | 6000 | 810000 | 0.6 | 0.486 | H2 (harness)
R0049 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | MMLU-Med | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 1089 | 4500 | 4900500 | 0.6 | 2.9403 | H2 (harness)
R0050 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | MMLU-Med | 123 | Pending |  |  |  | — | off | off | 32 | 1 | 1089 | 4500 | 4900500 | 0.6 | 2.9403 | H2 (harness)
R0051 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | MMLU-Med | 7 | Pending |  |  |  | — | off | off | 32 | 1 | 1089 | 4500 | 4900500 | 0.6 | 2.9403 | H2 (harness)
R0052 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | MedQA-US | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 1273 | 5000 | 6365000 | 0.6 | 3.819 | H2 (harness)
R0053 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | MedQA-US | 123 | Pending |  |  |  | — | off | off | 32 | 1 | 1273 | 5000 | 6365000 | 0.6 | 3.819 | H2 (harness)
R0054 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | MedQA-US | 7 | Pending |  |  |  | — | off | off | 32 | 1 | 1273 | 5000 | 6365000 | 0.6 | 3.819 | H2 (harness)
R0055 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | MedMCQA | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 4183 | 4500 | 18823500 | 0.6 | 11.2941 | H2 (harness)
R0056 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | MedMCQA | 123 | Pending |  |  |  | — | off | off | 32 | 1 | 4183 | 4500 | 18823500 | 0.6 | 11.2941 | H2 (harness)
R0057 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | MedMCQA | 7 | Pending |  |  |  | — | off | off | 32 | 1 | 4183 | 4500 | 18823500 | 0.6 | 11.2941 | H2 (harness)
R0058 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | PubMedQA | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 500 | 5500 | 2750000 | 0.6 | 1.65 | H2 (harness)
R0059 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | PubMedQA | 123 | Pending |  |  |  | — | off | off | 32 | 1 | 500 | 5500 | 2750000 | 0.6 | 1.65 | H2 (harness)
R0060 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | PubMedQA | 7 | Pending |  |  |  | — | off | off | 32 | 1 | 500 | 5500 | 2750000 | 0.6 | 1.65 | H2 (harness)
R0061 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | BioASQ-YN | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 618 | 5000 | 3090000 | 0.6 | 1.854 | H2 (harness)
R0062 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | BioASQ-YN | 123 | Pending |  |  |  | — | off | off | 32 | 1 | 618 | 5000 | 3090000 | 0.6 | 1.854 | H2 (harness)
R0063 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | BioASQ-YN | 7 | Pending |  |  |  | — | off | off | 32 | 1 | 618 | 5000 | 3090000 | 0.6 | 1.854 | H2 (harness)
R0064 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | GraphRAG-Bench-Med | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 50 | 8000 | 400000 | 0.6 | 0.24 | H2 (harness)
R0065 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | GraphRAG-Bench-Med | 123 | Pending |  |  |  | — | off | off | 32 | 1 | 50 | 8000 | 400000 | 0.6 | 0.24 | H2 (harness)
R0066 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | GraphRAG-Bench-Med | 7 | Pending |  |  |  | — | off | off | 32 | 1 | 50 | 8000 | 400000 | 0.6 | 0.24 | H2 (harness)
R0067 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 200 | 8000 | 1600000 | 0.6 | 0.96 | H2 (harness)
R0068 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | Clinical-Set | 123 | Pending |  |  |  | — | off | off | 32 | 1 | 200 | 8000 | 1600000 | 0.6 | 0.96 | H2 (harness)
R0069 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | Clinical-Set | 7 | Pending |  |  |  | — | off | off | 32 | 1 | 200 | 8000 | 1600000 | 0.6 | 0.96 | H2 (harness)
R0070 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | OverRefusal | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 150 | 6000 | 900000 | 0.6 | 0.54 | H2 (harness)
R0071 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | OverRefusal | 123 | Pending |  |  |  | — | off | off | 32 | 1 | 150 | 6000 | 900000 | 0.6 | 0.54 | H2 (harness)
R0072 | P0 | P2 | T2 | Dense-MedCPT | Llama-70B | OverRefusal | 7 | Pending |  |  |  | — | off | off | 32 | 1 | 150 | 6000 | 900000 | 0.6 | 0.54 | H2 (harness)
R0073 | P0 | P2 | T2 | Graph-only | Llama-70B | MMLU-Med | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 1089 | 4500 | 3430350 | 0.6 | 2.0582 | G3 (grounded graph)
R0074 | P0 | P2 | T2 | Graph-only | Llama-70B | MMLU-Med | 123 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 1089 | 4500 | 3430350 | 0.6 | 2.0582 | G3 (grounded graph)
R0075 | P0 | P2 | T2 | Graph-only | Llama-70B | MMLU-Med | 7 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 1089 | 4500 | 3430350 | 0.6 | 2.0582 | G3 (grounded graph)
R0076 | P0 | P2 | T2 | Graph-only | Llama-70B | MedQA-US | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 1273 | 5000 | 4455500 | 0.6 | 2.6733 | G3 (grounded graph)
R0077 | P0 | P2 | T2 | Graph-only | Llama-70B | MedQA-US | 123 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 1273 | 5000 | 4455500 | 0.6 | 2.6733 | G3 (grounded graph)
R0078 | P0 | P2 | T2 | Graph-only | Llama-70B | MedQA-US | 7 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 1273 | 5000 | 4455500 | 0.6 | 2.6733 | G3 (grounded graph)
R0079 | P0 | P2 | T2 | Graph-only | Llama-70B | MedMCQA | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 4183 | 4500 | 13176450 | 0.6 | 7.9059 | G3 (grounded graph)
R0080 | P0 | P2 | T2 | Graph-only | Llama-70B | MedMCQA | 123 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 4183 | 4500 | 13176450 | 0.6 | 7.9059 | G3 (grounded graph)
R0081 | P0 | P2 | T2 | Graph-only | Llama-70B | MedMCQA | 7 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 4183 | 4500 | 13176450 | 0.6 | 7.9059 | G3 (grounded graph)
R0082 | P0 | P2 | T2 | Graph-only | Llama-70B | PubMedQA | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 500 | 5500 | 1925000 | 0.6 | 1.155 | G3 (grounded graph)
R0083 | P0 | P2 | T2 | Graph-only | Llama-70B | PubMedQA | 123 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 500 | 5500 | 1925000 | 0.6 | 1.155 | G3 (grounded graph)
R0084 | P0 | P2 | T2 | Graph-only | Llama-70B | PubMedQA | 7 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 500 | 5500 | 1925000 | 0.6 | 1.155 | G3 (grounded graph)
R0085 | P0 | P2 | T2 | Graph-only | Llama-70B | BioASQ-YN | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 618 | 5000 | 2163000 | 0.6 | 1.2978 | G3 (grounded graph)
R0086 | P0 | P2 | T2 | Graph-only | Llama-70B | BioASQ-YN | 123 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 618 | 5000 | 2163000 | 0.6 | 1.2978 | G3 (grounded graph)
R0087 | P0 | P2 | T2 | Graph-only | Llama-70B | BioASQ-YN | 7 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 618 | 5000 | 2163000 | 0.6 | 1.2978 | G3 (grounded graph)
R0088 | P0 | P2 | T2 | Graph-only | Llama-70B | GraphRAG-Bench-Med | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 50 | 8000 | 280000 | 0.6 | 0.168 | G3 (grounded graph)
R0089 | P0 | P2 | T2 | Graph-only | Llama-70B | GraphRAG-Bench-Med | 123 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 50 | 8000 | 280000 | 0.6 | 0.168 | G3 (grounded graph)
R0090 | P0 | P2 | T2 | Graph-only | Llama-70B | GraphRAG-Bench-Med | 7 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 50 | 8000 | 280000 | 0.6 | 0.168 | G3 (grounded graph)
R0091 | P0 | P2 | T2 | Graph-only | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 200 | 8000 | 1120000 | 0.6 | 0.672 | G3 (grounded graph)
R0092 | P0 | P2 | T2 | Graph-only | Llama-70B | Clinical-Set | 123 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 200 | 8000 | 1120000 | 0.6 | 0.672 | G3 (grounded graph)
R0093 | P0 | P2 | T2 | Graph-only | Llama-70B | Clinical-Set | 7 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 200 | 8000 | 1120000 | 0.6 | 0.672 | G3 (grounded graph)
R0094 | P0 | P2 | T2 | Graph-only | Llama-70B | OverRefusal | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 150 | 6000 | 630000 | 0.6 | 0.378 | G3 (grounded graph)
R0095 | P0 | P2 | T2 | Graph-only | Llama-70B | OverRefusal | 123 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 150 | 6000 | 630000 | 0.6 | 0.378 | G3 (grounded graph)
R0096 | P0 | P2 | T2 | Graph-only | Llama-70B | OverRefusal | 7 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 150 | 6000 | 630000 | 0.6 | 0.378 | G3 (grounded graph)
R0097 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | MMLU-Med | 42 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 1089 | 4500 | 5390550 | 0.6 | 3.2343 | G3 (grounded graph)
R0098 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | MMLU-Med | 123 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 1089 | 4500 | 5390550 | 0.6 | 3.2343 | G3 (grounded graph)
R0099 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | MMLU-Med | 7 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 1089 | 4500 | 5390550 | 0.6 | 3.2343 | G3 (grounded graph)
R0100 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | MedQA-US | 42 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | G3 (grounded graph)
R0101 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | MedQA-US | 123 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | G3 (grounded graph)
R0102 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | MedQA-US | 7 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | G3 (grounded graph)
R0103 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | MedMCQA | 42 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | G3 (grounded graph)
R0104 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | MedMCQA | 123 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | G3 (grounded graph)
R0105 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | MedMCQA | 7 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | G3 (grounded graph)
R0106 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | PubMedQA | 42 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | G3 (grounded graph)
R0107 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | PubMedQA | 123 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | G3 (grounded graph)
R0108 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | PubMedQA | 7 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | G3 (grounded graph)
R0109 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | BioASQ-YN | 42 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 618 | 5000 | 3399000 | 0.6 | 2.0394 | G3 (grounded graph)
R0110 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | BioASQ-YN | 123 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 618 | 5000 | 3399000 | 0.6 | 2.0394 | G3 (grounded graph)
R0111 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | BioASQ-YN | 7 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 618 | 5000 | 3399000 | 0.6 | 2.0394 | G3 (grounded graph)
R0112 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | GraphRAG-Bench-Med | 42 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 50 | 8000 | 440000 | 0.6 | 0.264 | G3 (grounded graph)
R0113 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | GraphRAG-Bench-Med | 123 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 50 | 8000 | 440000 | 0.6 | 0.264 | G3 (grounded graph)
R0114 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | GraphRAG-Bench-Med | 7 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 50 | 8000 | 440000 | 0.6 | 0.264 | G3 (grounded graph)
R0115 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | G3 (grounded graph)
R0116 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | Clinical-Set | 123 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | G3 (grounded graph)
R0117 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | Clinical-Set | 7 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | G3 (grounded graph)
R0118 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | OverRefusal | 42 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 150 | 6000 | 990000 | 0.6 | 0.594 | G3 (grounded graph)
R0119 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | OverRefusal | 123 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 150 | 6000 | 990000 | 0.6 | 0.594 | G3 (grounded graph)
R0120 | P0 | P2 | T2 | MedGraphRAG-repro | Llama-70B | OverRefusal | 7 | Pending |  |  |  | — | builtin | on | 2-hop | 1.1 | 150 | 6000 | 990000 | 0.6 | 0.594 | G3 (grounded graph)
R0121 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | MMLU-Med | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 1089 | 4500 | 5390550 | 0.6 | 3.2343 | H2 (harness)
R0122 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | MMLU-Med | 123 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 1089 | 4500 | 5390550 | 0.6 | 3.2343 | H2 (harness)
R0123 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | MMLU-Med | 7 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 1089 | 4500 | 5390550 | 0.6 | 3.2343 | H2 (harness)
R0124 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | MedQA-US | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | H2 (harness)
R0125 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | MedQA-US | 123 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | H2 (harness)
R0126 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | MedQA-US | 7 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | H2 (harness)
R0127 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | MedMCQA | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | H2 (harness)
R0128 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | MedMCQA | 123 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | H2 (harness)
R0129 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | MedMCQA | 7 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | H2 (harness)
R0130 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | PubMedQA | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | H2 (harness)
R0131 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | PubMedQA | 123 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | H2 (harness)
R0132 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | PubMedQA | 7 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | H2 (harness)
R0133 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | BioASQ-YN | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 618 | 5000 | 3399000 | 0.6 | 2.0394 | H2 (harness)
R0134 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | BioASQ-YN | 123 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 618 | 5000 | 3399000 | 0.6 | 2.0394 | H2 (harness)
R0135 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | BioASQ-YN | 7 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 618 | 5000 | 3399000 | 0.6 | 2.0394 | H2 (harness)
R0136 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | GraphRAG-Bench-Med | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 50 | 8000 | 440000 | 0.6 | 0.264 | H2 (harness)
R0137 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | GraphRAG-Bench-Med | 123 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 50 | 8000 | 440000 | 0.6 | 0.264 | H2 (harness)
R0138 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | GraphRAG-Bench-Med | 7 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 50 | 8000 | 440000 | 0.6 | 0.264 | H2 (harness)
R0139 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | H2 (harness)
R0140 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | Clinical-Set | 123 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | H2 (harness)
R0141 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | Clinical-Set | 7 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | H2 (harness)
R0142 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | OverRefusal | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 150 | 6000 | 990000 | 0.6 | 0.594 | H2 (harness)
R0143 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | OverRefusal | 123 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 150 | 6000 | 990000 | 0.6 | 0.594 | H2 (harness)
R0144 | P0 | P2 | T2 | Hybrid-RRF4 | Llama-70B | OverRefusal | 7 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 150 | 6000 | 990000 | 0.6 | 0.594 | H2 (harness)
R0145 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | MMLU-Med | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 1089 | 4500 | 5390550 | 0.6 | 3.2343 | G3 (grounded graph)
R0146 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | MMLU-Med | 123 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 1089 | 4500 | 5390550 | 0.6 | 3.2343 | G3 (grounded graph)
R0147 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | MMLU-Med | 7 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 1089 | 4500 | 5390550 | 0.6 | 3.2343 | G3 (grounded graph)
R0148 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | MedQA-US | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | G3 (grounded graph)
R0149 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | MedQA-US | 123 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | G3 (grounded graph)
R0150 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | MedQA-US | 7 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | G3 (grounded graph)
R0151 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | MedMCQA | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | G3 (grounded graph)
R0152 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | MedMCQA | 123 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | G3 (grounded graph)
R0153 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | MedMCQA | 7 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | G3 (grounded graph)
R0154 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | PubMedQA | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | G3 (grounded graph)
R0155 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | PubMedQA | 123 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | G3 (grounded graph)
R0156 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | PubMedQA | 7 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | G3 (grounded graph)
R0157 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | BioASQ-YN | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 618 | 5000 | 3399000 | 0.6 | 2.0394 | G3 (grounded graph)
R0158 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | BioASQ-YN | 123 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 618 | 5000 | 3399000 | 0.6 | 2.0394 | G3 (grounded graph)
R0159 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | BioASQ-YN | 7 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 618 | 5000 | 3399000 | 0.6 | 2.0394 | G3 (grounded graph)
R0160 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | GraphRAG-Bench-Med | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 50 | 8000 | 440000 | 0.6 | 0.264 | G3 (grounded graph)
R0161 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | GraphRAG-Bench-Med | 123 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 50 | 8000 | 440000 | 0.6 | 0.264 | G3 (grounded graph)
R0162 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | GraphRAG-Bench-Med | 7 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 50 | 8000 | 440000 | 0.6 | 0.264 | G3 (grounded graph)
R0163 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | G3 (grounded graph)
R0164 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | Clinical-Set | 123 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | G3 (grounded graph)
R0165 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | Clinical-Set | 7 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | G3 (grounded graph)
R0166 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | OverRefusal | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 150 | 6000 | 990000 | 0.6 | 0.594 | G3 (grounded graph)
R0167 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | OverRefusal | 123 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 150 | 6000 | 990000 | 0.6 | 0.594 | G3 (grounded graph)
R0168 | P0 | P3 | T3 | Hybrid-CARRF | Llama-70B | OverRefusal | 7 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 150 | 6000 | 990000 | 0.6 | 0.594 | G3 (grounded graph)
R0169 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | MMLU-Med | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 1089 | 4500 | 5635575 | 0.6 | 3.3813 | P3 gate + oracle labels
R0170 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | MMLU-Med | 123 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 1089 | 4500 | 5635575 | 0.6 | 3.3813 | P3 gate + oracle labels
R0171 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | MMLU-Med | 7 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 1089 | 4500 | 5635575 | 0.6 | 3.3813 | P3 gate + oracle labels
R0172 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | MedQA-US | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 1273 | 5000 | 7319750 | 0.6 | 4.3918 | P3 gate + oracle labels
R0173 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | MedQA-US | 123 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 1273 | 5000 | 7319750 | 0.6 | 4.3918 | P3 gate + oracle labels
R0174 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | MedQA-US | 7 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 1273 | 5000 | 7319750 | 0.6 | 4.3918 | P3 gate + oracle labels
R0175 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | MedMCQA | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 4183 | 4500 | 21647025 | 0.6 | 12.9882 | P3 gate + oracle labels
R0176 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | MedMCQA | 123 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 4183 | 4500 | 21647025 | 0.6 | 12.9882 | P3 gate + oracle labels
R0177 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | MedMCQA | 7 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 4183 | 4500 | 21647025 | 0.6 | 12.9882 | P3 gate + oracle labels
R0178 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | PubMedQA | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 500 | 5500 | 3162500 | 0.6 | 1.8975 | P3 gate + oracle labels
R0179 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | PubMedQA | 123 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 500 | 5500 | 3162500 | 0.6 | 1.8975 | P3 gate + oracle labels
R0180 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | PubMedQA | 7 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 500 | 5500 | 3162500 | 0.6 | 1.8975 | P3 gate + oracle labels
R0181 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | BioASQ-YN | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 618 | 5000 | 3553500 | 0.6 | 2.1321 | P3 gate + oracle labels
R0182 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | BioASQ-YN | 123 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 618 | 5000 | 3553500 | 0.6 | 2.1321 | P3 gate + oracle labels
R0183 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | BioASQ-YN | 7 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 618 | 5000 | 3553500 | 0.6 | 2.1321 | P3 gate + oracle labels
R0184 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | GraphRAG-Bench-Med | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 50 | 8000 | 460000 | 0.6 | 0.276 | P3 gate + oracle labels
R0185 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | GraphRAG-Bench-Med | 123 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 50 | 8000 | 460000 | 0.6 | 0.276 | P3 gate + oracle labels
R0186 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | GraphRAG-Bench-Med | 7 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 50 | 8000 | 460000 | 0.6 | 0.276 | P3 gate + oracle labels
R0187 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 200 | 8000 | 1840000 | 0.6 | 1.104 | P3 gate + oracle labels
R0188 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | Clinical-Set | 123 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 200 | 8000 | 1840000 | 0.6 | 1.104 | P3 gate + oracle labels
R0189 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | Clinical-Set | 7 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 200 | 8000 | 1840000 | 0.6 | 1.104 | P3 gate + oracle labels
R0190 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | OverRefusal | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 150 | 6000 | 1035000 | 0.6 | 0.621 | P3 gate + oracle labels
R0191 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | OverRefusal | 123 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 150 | 6000 | 1035000 | 0.6 | 0.621 | P3 gate + oracle labels
R0192 | P0 | P4 | T3 | Hybrid-CARRF-CARe | Llama-70B | OverRefusal | 7 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 150 | 6000 | 1035000 | 0.6 | 0.621 | P3 gate + oracle labels
R0193 | P2 | P3 | T3 | Hybrid-RRF2 | Llama-70B | MedQA-US | 42 | Pending |  |  |  | RRF-2 | off | on | 32 | 1 | 1273 | 5000 | 6365000 | 0.6 | 3.819 | H2 (harness)
R0194 | P2 | P3 | T3 | Hybrid-RRF2 | Llama-70B | MedMCQA | 42 | Pending |  |  |  | RRF-2 | off | on | 32 | 1 | 4183 | 4500 | 18823500 | 0.6 | 11.2941 | H2 (harness)
R0195 | P2 | P3 | T3 | Hybrid-RRF2 | Llama-70B | PubMedQA | 42 | Pending |  |  |  | RRF-2 | off | on | 32 | 1 | 500 | 5500 | 2750000 | 0.6 | 1.65 | H2 (harness)
R0196 | P2 | P3 | T3 | Hybrid-RRF2 | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | RRF-2 | off | on | 32 | 1 | 200 | 8000 | 1600000 | 0.6 | 0.96 | H2 (harness)
R0197 | P2 | P3 | T3 | Hybrid-CARRF-staticRerank | Llama-70B | MedQA-US | 42 | Pending |  |  |  | CA-RRF | static | on | 32 + 2-hop | 1.2 | 1273 | 5000 | 7638000 | 0.6 | 4.5828 | G3 (grounded graph)
R0198 | P2 | P3 | T3 | Hybrid-CARRF-staticRerank | Llama-70B | MedMCQA | 42 | Pending |  |  |  | CA-RRF | static | on | 32 + 2-hop | 1.2 | 4183 | 4500 | 22588200 | 0.6 | 13.5529 | G3 (grounded graph)
R0199 | P2 | P3 | T3 | Hybrid-CARRF-staticRerank | Llama-70B | PubMedQA | 42 | Pending |  |  |  | CA-RRF | static | on | 32 + 2-hop | 1.2 | 500 | 5500 | 3300000 | 0.6 | 1.98 | G3 (grounded graph)
R0200 | P2 | P3 | T3 | Hybrid-CARRF-staticRerank | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | CA-RRF | static | on | 32 + 2-hop | 1.2 | 200 | 8000 | 1920000 | 0.6 | 1.152 | G3 (grounded graph)
R0201 | P2 | P3 | T3 | Hybrid-CARRF-noVecIndex | Llama-70B | MedQA-US | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 1273 | 5000 | 7001500 | 0.6 | 4.2009 | G3 (grounded graph)
R0202 | P2 | P3 | T3 | Hybrid-CARRF-noVecIndex | Llama-70B | MedMCQA | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 4183 | 4500 | 20705850 | 0.6 | 12.4235 | G3 (grounded graph)
R0203 | P2 | P3 | T3 | Hybrid-CARRF-noVecIndex | Llama-70B | PubMedQA | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 500 | 5500 | 3025000 | 0.6 | 1.815 | G3 (grounded graph)
R0204 | P2 | P3 | T3 | Hybrid-CARRF-noVecIndex | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | CA-RRF | off | on | 32 + 2-hop | 1.1 | 200 | 8000 | 1760000 | 0.6 | 1.056 | G3 (grounded graph)
R0205 | P2 | P3 | T3 | Hybrid-CARRF-noGrounding | Llama-70B | MedQA-US | 42 | Pending |  |  |  | CA-RRF | off | off | 32 + 2-hop | 1 | 1273 | 5000 | 6365000 | 0.6 | 3.819 | G3 (grounded graph)
R0206 | P2 | P3 | T3 | Hybrid-CARRF-noGrounding | Llama-70B | MedMCQA | 42 | Pending |  |  |  | CA-RRF | off | off | 32 + 2-hop | 1 | 4183 | 4500 | 18823500 | 0.6 | 11.2941 | G3 (grounded graph)
R0207 | P2 | P3 | T3 | Hybrid-CARRF-noGrounding | Llama-70B | PubMedQA | 42 | Pending |  |  |  | CA-RRF | off | off | 32 + 2-hop | 1 | 500 | 5500 | 2750000 | 0.6 | 1.65 | G3 (grounded graph)
R0208 | P2 | P3 | T3 | Hybrid-CARRF-noGrounding | Llama-70B | Clinical-Set | 42 | Pending |  |  |  | CA-RRF | off | off | 32 + 2-hop | 1 | 200 | 8000 | 1600000 | 0.6 | 0.96 | G3 (grounded graph)
R0209 | P1 | P2 | T2 | Dense-MedCPT | Qwen-14B | MedQA-US | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 1273 | 5000 | 6365000 | 0.15 | 0.95475 | H2 (harness)
R0210 | P1 | P2 | T2 | Dense-MedCPT | Qwen-14B | PubMedQA | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 500 | 5500 | 2750000 | 0.15 | 0.4125 | H2 (harness)
R0211 | P1 | P2 | T2 | Dense-MedCPT | Qwen-14B | Clinical-Set | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 200 | 8000 | 1600000 | 0.15 | 0.24 | H2 (harness)
R0212 | P1 | P2 | T2 | Graph-only | Qwen-14B | MedQA-US | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 1273 | 5000 | 4455500 | 0.15 | 0.66832 | G3 (grounded graph)
R0213 | P1 | P2 | T2 | Graph-only | Qwen-14B | PubMedQA | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 500 | 5500 | 1925000 | 0.15 | 0.28875 | G3 (grounded graph)
R0214 | P1 | P2 | T2 | Graph-only | Qwen-14B | Clinical-Set | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 200 | 8000 | 1120000 | 0.15 | 0.168 | G3 (grounded graph)
R0215 | P1 | P2 | T2 | Hybrid-RRF4 | Qwen-14B | MedQA-US | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 1273 | 5000 | 7001500 | 0.15 | 1.0502 | H2 (harness)
R0216 | P1 | P2 | T2 | Hybrid-RRF4 | Qwen-14B | PubMedQA | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 500 | 5500 | 3025000 | 0.15 | 0.45375 | H2 (harness)
R0217 | P1 | P2 | T2 | Hybrid-RRF4 | Qwen-14B | Clinical-Set | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 200 | 8000 | 1760000 | 0.15 | 0.264 | H2 (harness)
R0218 | P1 | P4 | T3 | Hybrid-CARRF-CARe | Qwen-14B | MedQA-US | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 1273 | 5000 | 7319750 | 0.15 | 1.098 | P3 gate + oracle labels
R0219 | P1 | P4 | T3 | Hybrid-CARRF-CARe | Qwen-14B | PubMedQA | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 500 | 5500 | 3162500 | 0.15 | 0.47437 | P3 gate + oracle labels
R0220 | P1 | P4 | T3 | Hybrid-CARRF-CARe | Qwen-14B | Clinical-Set | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 200 | 8000 | 1840000 | 0.15 | 0.276 | P3 gate + oracle labels
R0221 | P1 | P2 | T2 | Dense-MedCPT | Mistral-24B | MedQA-US | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 1273 | 5000 | 6365000 | 0.2 | 1.273 | H2 (harness)
R0222 | P1 | P2 | T2 | Dense-MedCPT | Mistral-24B | PubMedQA | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 500 | 5500 | 2750000 | 0.2 | 0.55 | H2 (harness)
R0223 | P1 | P2 | T2 | Dense-MedCPT | Mistral-24B | Clinical-Set | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 200 | 8000 | 1600000 | 0.2 | 0.32 | H2 (harness)
R0224 | P1 | P2 | T2 | Graph-only | Mistral-24B | MedQA-US | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 1273 | 5000 | 4455500 | 0.2 | 0.8911 | G3 (grounded graph)
R0225 | P1 | P2 | T2 | Graph-only | Mistral-24B | PubMedQA | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 500 | 5500 | 1925000 | 0.2 | 0.385 | G3 (grounded graph)
R0226 | P1 | P2 | T2 | Graph-only | Mistral-24B | Clinical-Set | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 200 | 8000 | 1120000 | 0.2 | 0.224 | G3 (grounded graph)
R0227 | P1 | P2 | T2 | Hybrid-RRF4 | Mistral-24B | MedQA-US | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 1273 | 5000 | 7001500 | 0.2 | 1.4003 | H2 (harness)
R0228 | P1 | P2 | T2 | Hybrid-RRF4 | Mistral-24B | PubMedQA | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 500 | 5500 | 3025000 | 0.2 | 0.605 | H2 (harness)
R0229 | P1 | P2 | T2 | Hybrid-RRF4 | Mistral-24B | Clinical-Set | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 200 | 8000 | 1760000 | 0.2 | 0.352 | H2 (harness)
R0230 | P1 | P4 | T3 | Hybrid-CARRF-CARe | Mistral-24B | MedQA-US | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 1273 | 5000 | 7319750 | 0.2 | 1.464 | P3 gate + oracle labels
R0231 | P1 | P4 | T3 | Hybrid-CARRF-CARe | Mistral-24B | PubMedQA | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 500 | 5500 | 3162500 | 0.2 | 0.6325 | P3 gate + oracle labels
R0232 | P1 | P4 | T3 | Hybrid-CARRF-CARe | Mistral-24B | Clinical-Set | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 200 | 8000 | 1840000 | 0.2 | 0.368 | P3 gate + oracle labels
R0233 | P1 | P2 | T2 | Dense-MedCPT | BioMed-8B | MedQA-US | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 1273 | 5000 | 6365000 | 0.1 | 0.6365 | H2 (harness)
R0234 | P1 | P2 | T2 | Dense-MedCPT | BioMed-8B | PubMedQA | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 500 | 5500 | 2750000 | 0.1 | 0.275 | H2 (harness)
R0235 | P1 | P2 | T2 | Dense-MedCPT | BioMed-8B | Clinical-Set | 42 | Pending |  |  |  | — | off | off | 32 | 1 | 200 | 8000 | 1600000 | 0.1 | 0.16 | H2 (harness)
R0236 | P1 | P2 | T2 | Graph-only | BioMed-8B | MedQA-US | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 1273 | 5000 | 4455500 | 0.1 | 0.44555 | G3 (grounded graph)
R0237 | P1 | P2 | T2 | Graph-only | BioMed-8B | PubMedQA | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 500 | 5500 | 1925000 | 0.1 | 0.1925 | G3 (grounded graph)
R0238 | P1 | P2 | T2 | Graph-only | BioMed-8B | Clinical-Set | 42 | Pending |  |  |  | — | off | on | 2-hop | 0.7 | 200 | 8000 | 1120000 | 0.1 | 0.112 | G3 (grounded graph)
R0239 | P1 | P2 | T2 | Hybrid-RRF4 | BioMed-8B | MedQA-US | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 1273 | 5000 | 7001500 | 0.1 | 0.70015 | H2 (harness)
R0240 | P1 | P2 | T2 | Hybrid-RRF4 | BioMed-8B | PubMedQA | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 500 | 5500 | 3025000 | 0.1 | 0.3025 | H2 (harness)
R0241 | P1 | P2 | T2 | Hybrid-RRF4 | BioMed-8B | Clinical-Set | 42 | Pending |  |  |  | RRF-4 | off | on | 32 | 1.1 | 200 | 8000 | 1760000 | 0.1 | 0.176 | H2 (harness)
R0242 | P1 | P4 | T3 | Hybrid-CARRF-CARe | BioMed-8B | MedQA-US | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 1273 | 5000 | 7319750 | 0.1 | 0.73198 | P3 gate + oracle labels
R0243 | P1 | P4 | T3 | Hybrid-CARRF-CARe | BioMed-8B | PubMedQA | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 500 | 5500 | 3162500 | 0.1 | 0.31625 | P3 gate + oracle labels
R0244 | P1 | P4 | T3 | Hybrid-CARRF-CARe | BioMed-8B | Clinical-Set | 42 | Pending |  |  |  | CA-RRF | adaptive | on | 32 + 2-hop | 1.15 | 200 | 8000 | 1840000 | 0.1 | 0.184 | P3 gate + oracle labels

## Conditions
condition | retrievers | fusion | rerank | grounding | ctx_factor | serves | type | notes
No-RAG | none (closed-book) | — | off | off | 0.05 | Parametric floor | Baseline | Lower bound; isolates parametric knowledge.
BM25 | BM25 lexical | — | off | off | 0.9 | Lexical ceiling | Baseline | Sparse-only retrieval.
Dense-MedCPT | MedCPT | — | off | off | 1 | Dense ceiling | Baseline | Biomedical dense retriever.
Graph-only | Graph traversal | — | off | on | 0.7 | Structural selection | Baseline | Graph summaries/relations only; compact context.
MedGraphRAG-repro | Triple-graph + U-Retrieval | — | builtin | on | 1.1 | SOTA anchor | SOTA | Faithful reproduction; time-boxed (B3).
Hybrid-RRF2 | BM25 + MedCPT | RRF-2 | off | on | 1 | Fusion baseline | Baseline | Field-default 2-way fusion.
Hybrid-RRF4 | BM25+Contriever+SPECTER+MedCPT | RRF-4 | off | on | 1.1 | Strong baseline | Baseline | Field-default 4-way fusion.
Hybrid-CARRF | + Graph + UMLS-concept list | CA-RRF | off | on | 1.1 | C2 (concept fusion) | Contribution | Concept-overlap as a 1st-class fusion signal.
Hybrid-CARRF-staticRerank | + Concept | CA-RRF | static | on | 1.2 | Rerank ablation | Ablation | Always-on cross-encoder rerank.
Hybrid-CARRF-CARe | + Concept | CA-RRF | adaptive | on | 1.15 | C3 (adaptive rerank) — HEADLINE | Contribution | Per-query gate; cost-aware reranking.
Hybrid-CARRF-noVecIndex | + Concept (flat dense) | CA-RRF | off | on | 1.1 | Vector-index ablation | Ablation | Tests value of the ANN vector index.
Hybrid-CARRF-noGrounding | + Concept (no UMLS) | CA-RRF | off | off | 1 | Grounding ablation | Ablation | Tests value of UMLS grounding.

## Benchmarks
benchmark | name | source | type | n_items | tokens/item | role | metric_focus | governance
MMLU-Med | MMLU clinical subset | MIRAGE | MCQ | 1089 | 4500 | Exam-style reasoning | Generation | Public
MedQA-US | USMLE 4-option | MIRAGE | MCQ | 1273 | 5000 | Multi-step reasoning | Generation | Public
MedMCQA | AIIMS/NEET | MIRAGE | MCQ | 4183 | 4500 | Broad subject coverage | Generation | Public
PubMedQA | Reasoning-required | MIRAGE | yes/no/maybe | 500 | 5500 | Evidence-grounded QA | Retrieval+Gen | Public
BioASQ-YN | BioASQ Task B | MIRAGE | yes/no | 618 | 5000 | Fact verification | Retrieval+Gen | Public
GraphRAG-Bench-Med | GraphRAG-Bench (medical) | External | long-form | 50 | 8000 | Graph-stress reasoning | Retrieval+Gen | Public
Clinical-Set | Governance-clean discharge QA | Own | long-form | 200 | 8000 | Patient multi-span/temporal | Retrieval+Gen | DUA/synthetic — see R1
OverRefusal | Over-refusal / faithfulness slice | Curated | mixed | 150 | 6000 | Safety / grounding guard | Grounding | Public/curated
|  |  | TOTAL items | 8063

## Backbones
backbone | model_id | provider | role | context | rate $/M (est.) | notes
Llama-70B | meta/llama-3.3-70b-instruct | NVIDIA NIM (hosted) | Primary | 128k | 0.6 | Primary backbone for all main runs.
Qwen-14B | Qwen2.5-14B-Instruct | Local vLLM | Zoo | 32k | 0.15 | Mid-size open model (RGD generality).
Mistral-24B | Mistral-Small-3 24B | Local vLLM | Zoo | 32k | 0.2 | Alternative family (RGD generality).
BioMed-8B | Biomedical-tuned Llama-3.1-8B | Local vLLM | Zoo | 8k | 0.1 | Domain-tuned contrast (RGD generality).

## Metrics
metric | family | applies_to | direction | primary | how_computed
Recall@1 | Retrieval | Retrieval+Gen benchmarks | Higher |  | Gold doc in top-1
Recall@3 | Retrieval | Retrieval+Gen benchmarks | Higher | YES | Gold doc in top-3
Recall@5 | Retrieval | Retrieval+Gen benchmarks | Higher |  | Gold doc in top-5
Recall@10 | Retrieval | Retrieval+Gen benchmarks | Higher |  | Gold doc in top-10
Precision@3 | Retrieval | Retrieval+Gen benchmarks | Higher |  | Relevant fraction in top-3
MRR | Retrieval | Retrieval+Gen benchmarks | Higher | YES | Mean reciprocal rank of first gold
nDCG@10 | Retrieval | Retrieval+Gen benchmarks | Higher | YES | Graded ranking quality
Accuracy | Generation | MCQ / yes-no | Higher | YES | Correct option / label rate
Exact Match | Generation | All | Higher | YES | Normalized exact answer match (audited)
Token-F1 | Generation | All | Higher | YES | Token overlap F1
BERTScore-F1 | Generation | Long-form | Higher |  | Semantic similarity to reference
RAGAS-Faithfulness | Grounding | Free-text subset | Higher | YES | Answer supported by retrieved context (real RAGAS)
RAGAS-AnswerRelevance | Grounding | Free-text subset | Higher |  | Answer addresses the question
RAGAS-ContextPrecision | Grounding | Free-text subset | Higher |  | Useful fraction of retrieved context
RAGAS-ContextRecall | Grounding | Free-text subset | Higher |  | Coverage of needed evidence
Human-Faithfulness | Grounding | Human-rated subset | Higher | YES | Clinician/expert rubric (anchor for RAGAS)
Tokens/query | Cost | All | Lower |  | Mean total tokens per query
Latency-p50 (s) | Cost | All | Lower |  | Median end-to-end latency
Latency-p95 (s) | Cost | All | Lower | YES | Tail latency
USD/1k queries | Cost | All | Lower | YES | Operating cost per 1000 queries

## Statistics
Statistical protocol
Parameter | Value | Rationale
Seeds (headline conditions) | 42, 123, 7 | ≥3 runs for variance on every main comparison.
Seeds (ablation / zoo) | 42 | 1 seed; extend to 3 if a delta sits near its CI.
Bootstrap resamples | 10,000 | Per-metric 95% confidence intervals.
Significance test | Paired permutation (item-level) | Same items answered by all systems.
Permutations | ≥ 100,000 | Avoid the 1/N resolution floor; report EXACT p, never a floor.
Multiple-comparison correction | Holm–Bonferroni | Controls family-wise error across arms.
Effect size | Paired Cohen's d / Cliff's delta | Reported alongside every p-value.
Alpha | 0.05 | Two-sided.
CI reported for | All headline retrieval/gen/grounding metrics | See Metrics sheet, primary = YES.
Answer-format audit | Mandatory before any F1/EM claim | Resolves the thesis EM 0.00→0.76 anomaly.

## Budget_Summary
Compute & cost budget (live — recalculates from Run_Manifest)
All token/cost figures are engineering estimates; rates are per-1M-token blended estimates from the Backbones sheet.
By phase
phase | runs | est_tokens | est_cost $
P2 | 171 | 654967950 | 352.4781
P3 | 40 | 255151250 | 153.0908
P4 | 33 | 170926800 | 85.921
TOTAL | 244 | 1081046000 | 591.4899
With 1.5× rerun buffer |  | 1621569000 | 887.2348
+ grounding/RAGAS judge (post-hoc, free-text subset): budget ~70M tokens separately.
By condition
condition | runs | est_tokens | est_cost $
No-RAG | 24 | 5824350 | 3.4946
BM25 | 24 | 104838300 | 62.903
Dense-MedCPT | 33 | 148632000 | 74.7139
Graph-only | 33 | 104042400 | 52.2998
MedGraphRAG-repro | 24 | 128135700 | 76.8814
Hybrid-RRF2 | 4 | 29538500 | 17.7231
Hybrid-RRF4 | 33 | 163495200 | 82.1853
Hybrid-CARRF | 24 | 128135700 | 76.8814
Hybrid-CARRF-staticRerank | 4 | 35446200 | 21.2677
Hybrid-CARRF-CARe | 33 | 170926800 | 85.921
Hybrid-CARRF-noVecIndex | 4 | 32492350 | 19.4954
Hybrid-CARRF-noGrounding | 4 | 29538500 | 17.7231
By backbone
backbone | runs | est_tokens | est_cost $
Llama-70B | 208 | 954073250 | 572.4439
Qwen-14B | 12 | 42324250 | 6.3486
Mistral-24B | 12 | 42324250 | 8.4649
BioMed-8B | 12 | 42324250 | 4.2324
Live progress (updates as you set Status in Run_Manifest)
status | runs | % of total
Pending | 244 | 100%
Ready | 0 | 0%
Running | 0 | 0%
Done | 0 | 0%
Failed | 0 | 0%
Blocked | 0 | 0%
TOTAL | 244 | 100%

## Gates
Phase gates (go / no-go)
Gate | Day | Exit criteria | Status
End P1 | 10 | Governance locked (R1); harness validated on smoke set; clean graph build underway. | Pending
End P2 | 20 | Baselines + MedGraphRAG reproduced; grounded graph frozen; first RGD signal. | Pending
End P3 | 30 | CA-RRF ablation complete with confidence intervals. | Pending
End P4 | 40 | CARe gate trained; cost–quality frontier produced; model-zoo runs done. | Pending
End P5 | 50 | Full statistics locked; complete draft assembled; reproducibility package built. | Pending